## Slide 1: “STRENGTHENING THE ENTREPRENEURSHIP CULTURE AND COLLABORATION IN THE ELIGIBLE PROGRAMME AREA”
LIFELONG LEARNING CENTER ΟF REGION ΟF CENTRAL MACEDONIA SA
Presentation of PB2
Presenter: Kalathas Athanasios - Director
3rd meeting – Serres
15/12/2022

## Slide 2
Current status of performed activities
WP 1
Approved budget :12.440,01 €
Contracted : 12.440,01 €
Paid: 7.240,01 €
STRENGTHEN MILESTONES of the WP during the whole project |  |  | 
# | Title of the milestone | Ref. No. of the action (according the JOB) | STATUS
1 | Project coordination and technical meetings. | D1.2.2 | ON PROGRESS
2 | 3rd technical meeting | D.1.2.3 | IMPLEMENTED
3 | Auditing costs | D1.2.4 | SIGNED

## Slide 3
Current status of performed activities
WP 2
Approved budget :4.520,00 €
Contracted : 4.436,86 €
Paid: 1.366,58 €
STRENGTHEN MILESTONES of the WP during the whole project |  |  | 
# | Title of the milestone | Ref. No. of the action (according the JOB) | STATUS
1 | Promotion through Social Media. | D2.2.2 | ON PROGRESS
2 | Website | D.2.2.3 | ON PROGRESS
3 | Closing conference | D2.2.4 | SIGNED

## Slide 4
Current status of performed activities
WP 3
Approved budget :5.726,99 €
Contracted : 5.534,35 €
Paid: 1.004,4 €
STRENGTHEN MILESTONES of the WP during the whole project |  |  | 
# | Title of the milestone | Ref. No. of the action (according the JOB) | STATUS
1 | Participation in business mission in Blagoevgrad . | D3.2.1 | IMPLEMENTED
2 | Participation in two trade fairs | D.2.2.3 | IMPLEMENTED

## Slide 5
Current status of performed activities
WP 4
Approved budget :84.553,00 €
Contracted : 82.384,05 €
Paid: 59.293,16 €
STRENGTHEN MILESTONES of the WP during the whole project |  |  | 
# | Title of the milestone | Ref. No. of the action (according the JOB) | STATUS
1 | Training programs “Certified Executive of Food Safety & Quality Management” “Certified Export Trade Executive “ | D4.2.1 | IMPLEMENTED
2 | Best practice guide on cluster activities in EU leve | D.4.2.2 | IMPLEMENTED
3 | Organization of two workshops for the dissemination of best practices | D.4.2.2 | SIGNED

## Slide 6
Current status of performed activities
WP 5
Approved budget :15.250,00 €
Contracted : 15.087,55 €
Paid: 83,14 €
STRENGTHEN MILESTONES of the WP during the whole project |  |  | 
# | Title of the milestone | Ref. No. of the action (according the JOB) | STATUS
1 | Focus group in Serres, in the Building Materials / Construction industry | D5.2.1 | IMPLEMENTED
2 | Elaboration of common strategy and future action plan | D.5.2.2 | ON PROGRESS
3 | Participation in drafting the future collaboration agreements | D.5.2.3 | ΤΟ ΒΕ IMPLEMENTED

## Slide 7
Financial status of performed activities
WP | Deliv. No | Deliverable Title | Approved Budget | Contracted Budget | PAID | Verified Expenditure
1 | Del. 1.2.2 | Project Management | 10.145,00 € | 10.145,01 € | 6.776,34 € | 
1 | Del. 1.2.3 | Project Meetings | 795,00 € | 795,00 € | 91,67 € | 
1 | Del. 1.2.4 | Audit Costs | 1.500,00 € | 1.500,00 € | 372,00 € | 
2 | Del. 2.2.2 | Publicity material and promotion in social media | 2.200,00 € | 2.142,84 € | 194,80 € | 
2 | Del. 2.2.3 | Development of project website and content update | 2.000,00 € | 1.974,02 € | 749,78 € | 
2 | Del. 2.2.4 | Closing conference | 320,00 € | 320,00 € | 50,00 € | 
3 | Del.3.2.1 | Business missions and B2B meetings | 3.040,00 € | 3.040,00 € | 460,04 € | 
3 | Del. 3.2.2 | Participation in business fairs | 2.687,00 € | 2.494,36 € | 544,36 € | 
4 | Del. 4.2.1 | Training seminars | 68.570,00 € | 66.644,00 € | 55.034,60 € | 27.619,36
4 | Del. 4.2.2 | Informative workshops on the institution of cluster and dissemination of best practices | 15.983,00 € | 15.740,06 € | 4258,56 € | 
5 | Del. 5.2.1 | Meetings / focus groups to investigate the creation of competitive clusters | 4.000,00 € | 3.863,53 € | 83,14 € | 
5 | Del. 5.2.2 | Common strategy and future action plan | 8.350,00 € | 8.350,00 € |  | 
5 | Del. 5.2.3 | Future collaboration agreement | 2.900,00 € | 2.874,02 € |  | 
TOTAL |  |  | 122.490,00 € | 119.882,83 € | 68.615,29 € | 27.619,36 €

## Slide 8
  Planned activities till the end of project
  Contracting trainers for the training programs in Bulgaria
  Organization of two workshops for the dissemination of best practices on cluster activities in EU level
  Participation in the elaboration of common strategy and future action plan
  Participation in drafting the future collaboration agreement

## Slide 9
Thank you
for your attention!
Благодаря ви!
Σας ευχαριστώ!
https://www.kekpkm.gr/